## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 6 | 3
Project Circuit Schematic | Alaa | Done | 2 | 2
Drivers' Documentation | All Team | Done | 6 | 6
Low Level Design
Functions' Flowchart | All Team | Done | 6 | 5
Summary
Document File | Ahmed | Done | 2 | 4
Implementation
MCAL Module
DIO Driver | Alaa | Done | 1 | 1.5
EXI Driver | Alaa | Done | 1 | 3
TMR Driver | Ahmed | Done | 8 | 8
HAL Module
BTN Driver | Sarah | Done | 3 | 0.5
LCD Driver | Sarah | Done | 3 | 2
KPD Driver | Sarah | Done | 3 | 1
DELAY Driver | Ahmed | Done | 4 | 4
ICU Driver | Hossam | Done | 2 | 4
DCM Driver | Ahmed | Done | 4 | 4
PWM Driver | Ahmed | Done | 4 | 4
US Driver | Hossam | Done | 2 | 4
APP Module
App Driver | Alaa & Hossam | Done | 10 | 14
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 1 | 1
Unit Testing
Test MCAL | All Team | Done | 4 | 3
Test HAL | All Team | Done | 5 | 7
System Testing
Test APP | All Team | Done | 3 | 6
Final Requirements Review | All Team | Done | 2 | 3
Video
Video Recording | All Team | Done | 1 | 3
Video Editing | All Team | Done | 1 | 1

## Test Protocol
Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
APP Module
App Testing
TC_APP_001 | Test robot action when (distance > 70) | While robot is moving put an obstacle with distance more than 70 cm | Robot will move FWD with speed 30% for 5 seconds, if distance is still > 70 speed is increased to 50% | Matches Expected Result | Pass
TC_APP_002 | Test robot action when (distance 30-70) | While robot is moving put an obstacle at a distance between 30cm to 70 cm | Robot will move forward with speed 30% | Matches Expected Result | Pass
TC_APP_003 | Test robot action when (distance 20-30) | While robot is moving put an obstacle at a distance between 20cm to 30 cm | Robot will rotate 90deg in-place, check for obstacle, repeat if still at the same distance range (BONUS) if 360degrees has been completed and yet still there's an obstacle at the same distance range robot will stop for 3 seconds then check again. | Matches Expected Result | Pass
TC_APP_004 | Test robot action when (distance < 20) | While robot is moving put an obstacle at a distance less than 20cm | Robot will move backward with speed 30% | Matches Expected Result | Pass
TC_APP_005 | Test start button | repeat test cases from 1 to 6 and press the start button mid case | Only on welcome page robot will start, otherwise start button does nothing | Matches Expected Result | Pass
TC_APP_006 | Test button 0 | While in SET_DIR state, press button 0 | Expected that every press will toggle the preferred rotation direction (left/right) | Matches Expected Result | Pass
TC_APP_007 | Test stop button | repeat test cases from 1 to 6 and press the stop button mid case | App cancels everything, stops robot, go back to welcome page | Matches Expected Result | Pass